Digital Artifact Project Proposal: “The Truth, the Lies, and the Social Media”

Tyler Jung

Concept

I will create a podcast titled  “The Truth, the Lies, and the Social Media” (title work in progress). This podcast will focus on how social media platforms spread misinformation and create a false reality via echo chambers through reinforcing certain heavily biased views. This artifact aims to inform and educate the listeners about the mechanics behind this unfortunate, wide-spread phenomenon and its implications in the real world, and attempt to teach the listeners how to listen critically.

The podcast will aim to educate young adults who use social media often. I will use case studies, peer-reviewed articles, and research findings and interview peers to attempt to provide a wide and diverse perspective on how misinformation spreads and what can be done to notice it, and prevent the spread of it.

Episodes will be structured in this manner:

- Misinformation - how misinformation is formed and how it spreads so quickly.

- Echo Chamber - how misinformation can quickly form an echo chamber on certain communities such as Facebook and Reddit, and how this echo chamber can create false narratives and a digital divide.

- Objectivity - how to view information critically - tips and tricks on noticing misinformation and enabling social media users to think critically.

Podcast will aim to mix stories from interviewees, analysis of studies and research, and general interviews to keep the audio experience entertaining and informative.

Scope

The concept is three ten to twenty minute episodes, totalling to about 45 minutes to an hour. Each episode will be structured in:

- Brief introduction to the topic

- Main content using case studies, interviews, research findings, and anecdotes to keep the podcast interesting and informative

- A brief summary that reminds the listener of the topics that were discussed, and a hook for the next podcast episode.

I will use Audacity to record, and any music or sound effects I will produce myself if any.

Timeline

- Nov 11-15:

  - Get ideas for each episode

  - Reach out to potential interviewees.

  - Quick google scholar research and save interesting titles to be reviewed when I have time

- Nov 18-22:

  - Set up meetings for all interviewees

  - Finalise script for myself

  - Finalise Research from google scholar to be used in the podcast

  - Prepare interviewees for the podcast

- Nov 25-29

  - Record all episodes

- Dec 2-Deadline

  - Edit all episodes

  - Review series and re-record necessary parts

This schedule may be a little difficult with work (i’m putting in 50 hours a week on average) but I think it’s doable if I get the interviewees from work.

Final Submission

I will submit:

- 3 Episodes of the podcast

- A journal-like memo that details my experience through the 4 to 5 weeks

- Citation for all research used

Final thoughts

This podcast should be interesting to create and to consume, hopefully providing a decently informative guide to using social media in an educated manner.